CAPSTONE PROJECT REPORT

Report – Project Management Plan

– TPHCM, December 2025 –

# Table of Contents

I. Record of Changes

II. Project Management Plan

1. Overview

1.1 Scope & Estimation

1.2 Project Objectives

1.3 Project Risks

2. Management Approach

2.1 Project Process

2.2 Quality Management

2.3 Training Plan

3. Project Deliverables

4. Responsibility Assignments

5. Project Communications

6. Configuration Management

6.1 Document Management

6.2 Source Code Management

6.3 Tools & Infrastructures

# I. Record of Changes

| Date | A* / M, D | In charge | Change Description |
| --- | --- | --- | --- |
| 17/11/2025 | A | (Member name) | Add Quality Management, Training Plan |
| 17/11/2025 | A | (Member name) | Add project deliverables |
| 17/11/2025 | A | (Member name) | Add Responsibility Assignments |
| 17/11/2025 | A | (Member name) | Add project communication |
| 17/11/2025 | A | (Member name) | Add configuration management |
| 25/11/2025 | A | (Member name) | Add Scope & Estimation |
| 25/11/2025 | A | (Member name) | Add Overview |
| 25/11/2025 | A | (Member name) | Add Project process |
| 02/12/2025 | M | (Member name) | Edit Scope & Estimation |
| 02/12/2025 | M | (Member name) | Edit Project Objectives |
| 03/12/2025 | M | (Member name) | Edit Scope & Estimation |

*A - Added  M - Modified  D - Deleted

# II. Project Management Plan

## 1. Overview

### 1.1 Scope & Estimation

| # | WBS Item | Complexity | Est. Effort (man-days) |
| --- | --- | --- | --- |
| 1 | Feature 1: Authentication & User Management |  | 14 |
| 1.1 | Registration & login (JWT, refresh-token rotation) | Medium | 5 |
| 1.2 | Role-based access (Admin / Provider / Receiver / Volunteer) | Medium | 4 |
| 1.3 | Profile management | Simple | 5 |
| 2 | Feature 2: Food Listing Management (Provider) |  | 16 |
| 2.1 | Provider create / update listing with photos & details | Medium | 6 |
| 2.2 | Map-based pickup location picker (Mapbox) | Medium | 6 |
| 2.3 | Listing lifecycle & soft delete | Simple | 4 |
| 3 | Feature 3: Nearby Search & Reservation |  | 30 |
| 3.1 | PostGIS nearby search (ST_DWithin / ST_Distance) | Complex | 10 |
| 3.2 | Reservation with Redis lock + daily-limit check | Complex | 12 |
| 3.3 | QR code generation & scan-based handover | Medium | 8 |
| 4 | Feature 4: Delivery & Volunteer Coordination |  | 22 |
| 4.1 | Shipper offer dispatch (nearest shippers, 2-min expiry) | Complex | 10 |
| 4.2 | Volunteer availability & offer acceptance | Medium | 6 |
| 4.3 | Delivery tracking & status updates | Medium | 6 |
| 5 | Feature 5: Trust Score & Penalty System |  | 12 |
| 5.1 | Trust-score calculation & penalty rules | Medium | 6 |
| 5.2 | Auto restriction / ban + refresh-token revocation | Medium | 6 |
| 6 | Feature 6: Campaigns & Community Kitchen Operations |  | 12 |
| 6.1 | Campaign creation & management | Medium | 6 |
| 6.2 | Kitchen operations module | Medium | 6 |
| 7 | Feature 7: Real-time Notifications |  | 6 |
| 7.1 | WebSocket notifications + push delivery | Medium | 6 |
| 8 | Feature 8: Admin Dashboard & Verification |  | 10 |
| 8.1 | Admin verifies providers & manages users | Medium | 6 |
| 8.2 | System configuration management | Simple | 4 |
| 9 | Feature 9: Impact / ESG Reporting |  | 6 |
| 9.1 | ESG snapshot & impact dashboard | Medium | 6 |
|  | Total Estimated Effort (man-days) |  | 128 |

### 1.2 Project Objectives

Quality:

| # | Testing Stage | Test Coverage | No. of Defects | % of Defect | Notes |
| --- | --- | --- | --- | --- | --- |
| 1 | Reviewing | ≥ 95% requirements reviewed | ≤ 3 major | ≤ 5% | Review WBS, SRS, system & DB design, UI flow |
| 2 | Unit Test | ≥ 80% code coverage | ≤ 10 minor | ≤ 10% | FE + BE unit tests (listings, reservation, delivery, trust, notifications) |
| 3 | Integration Test | All modules integrated | ≤ 8 medium | ≤ 8% | Reservation ↔ Delivery ↔ Notification ↔ Trust modules |
| 4 | System Test | 100% major functions tested | ≤ 5 major | ≤ 5% | End-to-end: search → reserve → QR pickup → delivery → trust update |
| 5 | Acceptance Test | ≥ 95% test cases passed | 0 blocking defects | 0% | UAT with representative providers, receivers and volunteers |

Milestone Timeliness (%):

Target Timeliness: ≥ 90% milestones delivered on planned schedule

Maximum allowable deviation: 10%

Milestones considered: Requirements → Design → Implementation → Testing → Final Integration → Deployment

Allocated Effort (man-days):

| Activity | Allocated % | Estimated Man-days |
| --- | --- | --- |
| Requirements Analysis | 12% | 15.36 |
| System & UI/UX Design | 15% | 19.20 |
| Frontend Development (Web + Mobile) | 28% | 35.84 |
| Backend Development | 30% | 38.40 |
| Testing (Unit + Integration + System + UAT) | 12% | 15.36 |
| Project Management | 3% | 3.84 |
| Total | 100% | 128 |

### 1.3 Project Risks

| # | Risk Description | Impact | Possibility | Response Plans |
| --- | --- | --- | --- | --- |
| 1 | Concurrent reservations may cause double-booking of the same listing | High | Medium | Use Redis distributed lock + atomic transaction (decrement quantity & create reservation together) |
| 2 | PostGIS spatial queries may slow down as the number of listings grows | Medium | Medium | Add GiST spatial indexes, cache nearby results, bound search radius and result limits |
| 3 | Fraudulent or unsafe food listings may harm receivers | High | Medium | Provider verification by admin, trust-score penalties, reporting and food-safety violation handling |
| 4 | Low volunteer availability may delay or block deliveries | Medium | Medium | Offer expiry + re-dispatch to next nearest shippers, dedication points to incentivize volunteers |
| 5 | Real-time notification / delivery dispatch may fail under poor connectivity | Medium | Medium | Auto-reconnect WebSocket, retry via BullMQ queue, push-notification fallback |

## 2. Management Approach

FoodResQ follows an agile management approach: work is organized in short, iterative sprints, focusing on small, valuable increments, and the plan is adapted based on feedback rather than following a fixed, upfront schedule.

### 2.1 Project Process

Sprints 1–2: Foundation and Core Model (Weeks 1–4)

Define domain model: User, Role, FoodListing, Reservation, Delivery, VolunteerProfile, Campaign, TrustScore, Notification.

Build authentication (JWT + refresh-token rotation), JwtAuthGuard, RolesGuard, and basic listing browsing.

Set up infrastructure: PostgreSQL + PostGIS, Redis, Mapbox; decide push-notification approach (FCM).

Sprints 3–4: Listings & Reservation Features (Weeks 5–8)

Implement provider food-listing management (create, update, map location picker, soft delete).

Implement PostGIS nearby search (ST_DWithin) and reservation flow with Redis lock + daily-limit enforcement.

Add QR-code generation and scan-based handover; update class/sequence diagrams.

Sprints 5–6: Delivery, Trust & Real-time (Weeks 9–12)

Implement shipper offer dispatch (nearest available shippers, 2-min expiry) and volunteer acceptance/tracking.

Add trust-score & penalty system (no-show, late cancellation, food-safety violation) with auto restriction/ban.

Add real-time notifications (WebSocket + push) and community campaigns / kitchen operations.

Sprint 7: Stabilization and Documentation (Weeks 13–14)

End-to-end testing of flows: search → reserve → QR pickup → delivery → trust update.

Optimize performance for spatial queries and reservation concurrency; fix bugs.

Finalize documentation: class specs, sequence diagrams (reservation, delivery, trust), user guide, deployment guide.

### 2.2 Quality Management

Defect Prevention

Apply coding standards and best practices.

Use linters and static code analysis to detect errors early.

Provide team training to improve skills.

Reviewing

Every feature/bug fix must go through peer review on GitHub.

Focus on logic, readability, security, and performance.

Unit Testing

Write unit tests for all core modules.

Use Jest or equivalent testing tools. Target coverage: ≥ 80%.

Integration Testing

Test interactions between modules: Frontend ↔ Backend ↔ Database.

Use Postman or supertest for API testing.

System Testing

Conduct full system testing before release.

Include functional, performance, security testing, and User Acceptance Testing (UAT).

Continuous Improvement

Track and analyze issues/bugs on GitHub.

Hold retrospectives to learn from mistakes and improve processes.

### 2.3 Training Plan

| Training Area | Participants | When, Duration | Waiver Criteria |
| --- | --- | --- | --- |
| Next.js (React + SSR/SSG) | Web front-end developers who lack Next.js experience | Week 1–2, 3 sessions × 2 hours | Able to create pages, use API routes, and fetch data via SSR/SSG independently |
| NestJS (Back-end API framework) | Back-end developers | Week 1–2, 3 sessions × 2 hours | Able to create modules, controllers, services, and RESTful APIs independently |
| Expo + React Native | Mobile developers / front-end devs moving to mobile | Week 2–3, 4 sessions × 2 hours | Able to build components, use navigation, handle state, and fetch API data independently |
| Git & GitHub | All team members | Week 1, 2 sessions × 1.5 hours | Able to commit, push, pull, branch, merge, and resolve conflicts independently |
| PostgreSQL + PostGIS | Back-end developers | Week 2–3, 3 sessions × 2 hours | Able to design schema, write spatial queries, and integrate with NestJS via Prisma |
| Redis & BullMQ (caching, locks, queues) | Back-end developers | Week 3, 2 sessions × 2 hours | Able to use caching, distributed locks, and background jobs independently |
| Testing (Unit & Integration) | All developers | Week 3–4, 2 sessions × 2 hours | Able to write and run unit and integration tests using Jest or equivalent |

## 3. Project Deliverables

| # | Deliverable | Due Date | Notes |
| --- | --- | --- | --- |
| 1 | Project Introduction Document | 10/12/2025 | Overview, objectives, scope, and team roles |
| 2 | Software Requirements Specification (SRS) – Overview | 10/12/2025 | High-level system requirements |
| 3 | SRS – User Requirements | 10/12/2025 | Detailed functional and non-functional requirements |
| 4 | Major Features & Functional Requirements List | 10/12/2025 | Key features and highlight features |
| 5 | Limitations & Exclusions | 10/12/2025 | Define what is out of scope |
| 6 | Software Product Vision | 10/12/2025 | Concise statement of project purpose and intent |
| 7 | Configuration Management Plan | 10/12/2025 | Document & source-code versioning plan |
| 8 | Web Application (Admin + Provider portal) | 15/12/2025 | Next.js web app for admin and provider management |
| 9 | Mobile Application (Receiver + Volunteer) | 15/12/2025 | React Native + Expo app for receivers and volunteer shippers |
| 10 | Backend & API Services | 15/12/2025 | NestJS backend, PostgreSQL + PostGIS, Redis, WebSocket |
| 11 | Testing Documents & Test Cases | 15/12/2025 | Unit tests, integration tests, UAT plans |
| 12 | Final Report & Documentation Package | 14/12/2025 | Complete SRS, design docs, source code, installation guide |

## 4. Responsibility Assignments

Legend: R = Responsible, S = Support, D = Done/Doer, blank = Not involved

| Responsibility | Member 1 (Leader) | Member 2 | Member 3 | Member 4 |
| --- | --- | --- | --- | --- |
| Project Planning & Tracking | S | R | D | R |
| Prepare Project Introduction Document | R | S | D | R |
| Prepare SRS Document (Overview Part) | R |  | D | S |
| Prepare SRS Document (User Requirements) | R | R | D | S |
| Prepare Functional Requirements | D | D | S | S |
| Prepare Non-Functional Requirements | R |  | D |  |
| Prepare Major Features List | R | D | S | S |
| Prepare Limitations & Exclusions |  | R | S | D |
| Prepare Software Product Vision | R | D | R | S |
| Prepare Configuration Management Plan | S | D |  | R |
| Develop Web App (Admin/Provider) | S | S | D | R |
| Develop Mobile App (Receiver/Volunteer) | D | S | S | R |
| Develop Backend & API | D | S |  | S |
| Implement Reservation / Delivery Module | D | S |  | S |
| Testing & QA | S | S | D | S |
| Deployment & Release | D | S | S | S |
| Documentation Review & Finalization | R | R | D | R |

## 5. Project Communications

| Communication Item | Who / Target | Purpose | When, Frequency | Type, Tool, Method(s) |
| --- | --- | --- | --- | --- |
| Project Kickoff Meeting | Project Team, Supervisor | Align goals, roles, scope, schedule | Once, at project start | Meet offline |
| Weekly Progress Report | Project Team, Supervisor | Update on tasks completed, blockers, next steps | Weekly | Meet offline |
| Sprint Review / Demo | Project Team, Supervisor | Demonstrate completed features, gather feedback | Weekly | Meet offline |
| Code Review | Leader, Members | Ensure code quality and progress | As needed per commit | Git pull requests / GitHub |
| Documentation Updates | Project Team | Keep SRS, design docs, test plans up-to-date | Ongoing | Google Drive |
| Issue Tracking & Bug Reporting | Project Team, Supervisor | Report, assign, and track bugs or issues | As issues arise | GitHub |

## 6. Configuration Management

### 6.1 Document Management

All project documents (SRS, design, test cases, user manuals, reports) are managed using version-controlled document storage.

Each document has a unique version number and date of modification.

Changes are tracked with a changelog specifying the author, modification date, and description of changes.

Documents are stored on a shared cloud repository (e.g., Google Drive) accessible to all team members.

Periodic reviews and approvals ensure documents remain accurate and up-to-date.

### 6.2 Source Code Management

All source code is managed using Git and hosted on GitHub.

Each feature, bug fix, or update is implemented on a separate branch and merged to main only after peer review and testing.

Commit messages follow a consistent format describing changes clearly.

Version tags are created for major releases or milestones.

Continuous integration (CI) tools can be optionally used to ensure builds are automated and stable.

Regular backups are maintained to prevent data loss.

### 6.3 Tools & Infrastructures

| Category | Tools / Infrastructure |
| --- | --- |
| Technology | Next.js (Web), React Native + Expo (Mobile App), NestJS (Backend) |
| Database | PostgreSQL + PostGIS |
| Caching / Queue / Real-time | Redis, BullMQ, Socket.IO (WebSocket) |
| IDEs/Editors | Visual Studio Code, Cursor, Notepad++ |
| Diagramming | PlantUML, DrawIO |
| Documentation | Microsoft Office, Google Docs/Sheets/Slides |
| Version Control | GitHub (Source Code), Google Drive (Documents) |
| Deployment server | Vercel (Web), Railway (Backend / Database / Redis) |
| Project management | Notion |